## Sheet1
Titel: | Graph Learning |  | Status
Work load | 6 x 30 h x 4 people = 720 h | Workload
| Nasim Uddin Ahmed | nasim.ahmed@st.ovgu.de
| Rahul Mondal | rahul.mondal@st.ovgu.de
| Minh Dung Do | minh.do@st.ovgu.de
| Yumna Iqbal | yumna.iqbal@st.ovgu.de
| Taha Bin Imran | taha.imran@st.ovgu.de
| Seles Selvan | seles.selvan@st.ovgu.de
GOAL (SMART) | Prototyping of application of ML directly on a graph database. Fullfill the milestones to show feasibility and possibilities.
Milestone 1 | KickOff presentation about the whole project and the team (40 h) | 40 | Done
Milestone 2 | Survey of graph-databases and data organisation (40 h) Detailled decription of neo4j focussing on data access for machine learning and GPU computing (80 h) | 120 | The end of December
Milestone 3 | Survey of implementations for decision tree learning and neuronal networks (40h) Implementation of decision tree learning algorithm in Java (80h) Evaluation of decision tree learning algorithm against the results of a standard library (40h) | 160
Milestone 4 | Apply decision tree learning algorithm directly on graph and compare the performance | 160
(Bonus)
Milestone 5 | Sum up all results in a 8-10 page paper (100 h) --> Bonus if publication could be really published in cooperation with D. Micheel | 120
Milestone 6 | Give a final presentation (20 h) | 20
Project management | 10-20% of the project | 100
| Sum | 720
Weekly Meeting | Description | Result
Datum
2020-11-24 | Kick-OFF,
Care about project management, Plan how to proceed, marks https://shiny.rstudio.com/ Dashboard starting template, Input and siginficance threshold, + wiki